## Start Here
IAMONIT Project Control Workbook
Jira-style sprint board + dependencies/timeline + IntelliJ-ready coding tasks
What this workbook gives you
A practical replacement for Jira: backlog, sprint board, timeline, dependencies, architecture, coding tasks by file/class, API, DB, risks, and release checklist.
How to use it
Start from Dashboard, then manage work in Sprint Board and Backlog. Use Dependencies & Timeline before assigning sprint dates. Use IntelliJ Coding Tasks when you are ready to code file-by-file.
Suggested stack
Next.js + Tailwind frontend, NestJS backend, PostgreSQL/Supabase, Supabase Storage/S3, JWT/RLS, Vercel + Railway/Render/AWS deployment.
Status values
Todo, In Progress, Blocked, Review, Done

## Dashboard
Project Dashboard
High-level project health, sprint progress, and delivery controls
Total Tasks |  |  | Done |  |  | In Progress
70 |  |  | 11 |  |  | 1
Blocked |  |  | Total Points |  |  | Done Points
0 |  |  | 369 |  |  | 45
Sprint | Tasks | Done | Blocked | Points | Completion % |  | Status | Count
Sprint 1 | 9 | 8 | 0 | 35 | 88.89% |  | Todo | 61
Sprint 2 | 9 | 1 | 0 | 47 | 11.11% |  | In Progress | 1
Sprint 3 | 7 | 0 | 0 | 31 | 0% |  | Blocked | 0
Sprint 4 | 10 | 0 | 0 | 58 | 0% |  | Review | 0
Sprint 5 | 8 | 0 | 0 | 53 | 0% |  | Done | 11
Sprint 6 | 8 | 0 | 0 | 34 | 0%
Sprint 7 | 7 | 0 | 0 | 47 | 0%
Sprint 8 | 7 | 0 | 0 | 27 | 0%
Sprint 9 | 5 | 0 | 0 | 26 | 0%

## Backlog
Task ID | Epic | Title | Priority | Story Points | Status | Description | Acceptance Criteria | Owner Role | Start Date | Sprint | Duration Days | End Date | Dependencies | Files / Classes | Notes
IAM-001 | Project Setup | Initialize Git repositories | Critical | 3 | Done | Create mono-repo or two repos for frontend/backend with branch rules. | Repos created; README exists; main/dev branches; .gitignore committed | DevOps | 2026-05-11 | Sprint 1 | 1 | 2026-05-11 |  | /README.md; /.gitignore
IAM-002 | Project Setup | Create Next.js app | Critical | 5 | Done | Initialize the Next.js frontend under apps/web using TypeScript, App Router, Tailwind CSS, and ESLint as part of the existing pnpm workspace. | apps/web/package.json exists; TypeScript is configured; App Router is configured; Tailwind CSS is configured; ESLint is configured; apps/web/app/layout.tsx exists; apps/web/app/page.tsx exists; the package participates in the existing pnpm workspace; the existing root dev:web command works with the web package; pnpm --filter <web-package> build passes | Frontend | 2026-05-11 | Sprint 1 | 2 | 2026-05-12 | IAM-001 | apps/web/package.json; apps/web/app/layout.tsx; apps/web/tailwind.config.ts
IAM-003 | Project Setup | Create NestJS backend | Critical | 5 | Done | Initialize NestJS TypeScript API service with modules folder. | API starts locally; health endpoint returns OK; Swagger enabled | Backend | 2026-05-11 | Sprint 1 | 2 | 2026-05-12 | IAM-001 | apps/api/src/main.ts; apps/api/src/app.module.ts
IAM-004 | Project Setup | Configure environment management | High | 3 | Done | Create .env examples and config validation for frontend/backend. | No secrets committed; env schema validates required values | DevOps | 2026-05-12 | Sprint 1 | 1 | 2026-05-12 | IAM-002,IAM-003 | apps/api/src/config/env.ts; apps/web/.env.example
IAM-005 | Project Setup | Setup code quality tools | High | 3 | Todo | Add ESLint, Prettier, lint scripts, formatting rules. | npm run lint passes; consistent formatting | DevOps | 2026-05-12 | Sprint 1 | 1 | 2026-05-12 | IAM-002,IAM-003 | apps/web/.eslintrc; apps/api/.eslintrc
IAM-006 | Database Foundation | Create Supabase project | Critical | 3 | Done | Provision Supabase project and connection settings. | DB reachable; connection string configured; local migration flow documented | Database | 2026-05-13 | Sprint 1 | 1 | 2026-05-13 | IAM-004 | supabase/config.toml
IAM-007 | Database Foundation | Create base audit trigger | High | 5 | Done | Add timestamptz audit fields and reusable trigger function. | created_at/updated_at use timestamptz; trigger tested | Database | 2026-05-13 | Sprint 1 | 2 | 2026-05-14 | IAM-006 | supabase/migrations/001_audit.sql
IAM-008 | Auth | Build auth DTOs and validation | High | 3 | Done | Create register/login DTOs with validation rules. | Invalid payloads rejected; password/email rules enforced | Backend | 2026-05-14 | Sprint 1 | 1 | 2026-05-14 | IAM-003 | apps/api/src/modules/auth/dto/register.dto.ts; login.dto.ts
IAM-009 | Auth | Auth UI shell | High | 5 | Done | Create login/register pages with role selection. | User can navigate between login/register; form validation visible | Frontend | 2026-05-14 | Sprint 1 | 2 | 2026-05-15 | IAM-002 | apps/web/app/(auth)/login/page.tsx; apps/web/app/(auth)/register/page.tsx
IAM-010 | Multi-Tenant Schema | Create tenants table | Critical | 5 | Done | Create tenants table with audit fields and unique name constraints. | Migration applies; tenant can be inserted; RLS enabled | Database | 2026-05-16 | Sprint 2 | 1 | 2026-05-16 | IAM-007 | supabase/migrations/010_tenants.sql
IAM-011 | Multi-Tenant Schema | Create app_users table | Critical | 5 | Done | Create app user profile linked to Supabase auth.users. | User profile linked to auth ID; role column constrained | Database | 2026-05-16 | Sprint 2 | 1 | 2026-05-16 | IAM-010 | supabase/migrations/011_users.sql
IAM-012 | Multi-Tenant Schema | Create transporter profiles table | High | 3 | Todo | Store company/dispatch/broker information by tenant. | Profile belongs to tenant; audit fields exist | Database | 2026-05-17 | Sprint 2 | 1 | 2026-05-17 | IAM-010 | supabase/migrations/012_transporter_profiles.sql
IAM-013 | Multi-Tenant Schema | Create car puller profiles table | High | 3 | Todo | Store car puller name/photo/logo/phone details. | Profile belongs to tenant/user; photo_url/logo_url supported | Database | 2026-05-17 | Sprint 2 | 1 | 2026-05-17 | IAM-011 | supabase/migrations/013_car_puller_profiles.sql
IAM-014 | Multi-Tenant Security | Implement tenant RLS policies | Critical | 8 | Todo | Add RLS policies for tenants, users, profiles. | Tenant A cannot query Tenant B data; policy tests pass | Security | 2026-05-18 | Sprint 2 | 2 | 2026-05-19 | IAM-010,IAM-011,IAM-012,IAM-013 | supabase/migrations/014_rls_core.sql
IAM-015 | Auth | Implement register company flow | Critical | 8 | Todo | Backend creates tenant + first admin user. | New transporter creates tenant; first user becomes admin | Backend | 2026-05-18 | Sprint 2 | 2 | 2026-05-19 | IAM-008,IAM-010,IAM-011 | apps/api/src/modules/auth/auth.service.ts; tenants.service.ts
IAM-016 | Auth | Implement login flow | Critical | 5 | Todo | Backend validates credentials and returns session/JWT context. | Valid login works; invalid login returns safe error; tenant_id included | Backend | 2026-05-19 | Sprint 2 | 2 | 2026-05-20 | IAM-008,IAM-011 | apps/api/src/modules/auth/auth.controller.ts; jwt.strategy.ts
IAM-017 | Frontend Auth | Connect login/register UI to API | High | 5 | Todo | Wire forms to auth endpoints and store session safely. | Successful login redirects; errors displayed; loading states exist | Frontend | 2026-05-20 | Sprint 2 | 2 | 2026-05-21 | IAM-009,IAM-015,IAM-016 | apps/web/lib/auth.ts; apps/web/app/(auth)/*
IAM-018 | Authorization | Create auth guard and role guard | Critical | 5 | Todo | Protect backend routes by JWT and roles. | Unauthorized blocked; forbidden roles blocked | Backend | 2026-05-20 | Sprint 2 | 2 | 2026-05-21 | IAM-016 | apps/api/src/common/guards/auth.guard.ts; roles.guard.ts
IAM-019 | Tenant Invitations | Create invitations table | High | 3 | Todo | Store tenant invitations with token, role, email, expiry. | Tokens unique; accepted flag supported; RLS enabled | Database | 2026-05-22 | Sprint 3 | 1 | 2026-05-22 | IAM-014 | supabase/migrations/019_invitations.sql
IAM-020 | Tenant Invitations | Build invite user API | High | 5 | Todo | Admin can invite dispatcher/car puller to tenant. | Invite created; duplicate invite handled; admin only | Backend | 2026-05-22 | Sprint 3 | 2 | 2026-05-23 | IAM-018,IAM-019 | apps/api/src/modules/invitations/invitations.controller.ts; invitations.service.ts
IAM-021 | Tenant Invitations | Build accept invitation API | High | 5 | Todo | User can accept invitation and join tenant. | Valid token assigns tenant; expired token rejected | Backend | 2026-05-23 | Sprint 3 | 2 | 2026-05-24 | IAM-020 | apps/api/src/modules/invitations/invitations.service.ts
IAM-022 | User Management | Build users list API | High | 3 | Todo | Admin can list users in same tenant. | Only tenant users returned; pagination exists | Backend | 2026-05-24 | Sprint 3 | 1 | 2026-05-24 | IAM-018 | apps/api/src/modules/users/users.controller.ts; users.service.ts
IAM-023 | User Management | Build user management UI | Medium | 5 | Todo | Users page with invite modal and role display. | Admin sees users; invite modal works; validation shown | Frontend | 2026-05-25 | Sprint 3 | 2 | 2026-05-26 | IAM-017,IAM-020,IAM-022 | apps/web/app/(dashboard)/users/page.tsx; components/users/InviteUserModal.tsx
IAM-024 | Layout | Create dashboard layout | High | 5 | Todo | Sidebar, topbar, tenant name, user menu, responsive layout. | Mobile and desktop usable; navigation links work | Frontend | 2026-05-24 | Sprint 3 | 2 | 2026-05-25 | IAM-017 | apps/web/app/(dashboard)/layout.tsx; components/layout/Sidebar.tsx; Topbar.tsx
IAM-025 | Profile | Build transporter profile API/UI | Medium | 5 | Todo | Allow admin to view/update company dispatch and broker info. | Profile saves; audit fields update; tenant isolated | Fullstack | 2026-05-26 | Sprint 3 | 2 | 2026-05-27 | IAM-012,IAM-018,IAM-024 | apps/api/src/modules/tenants/*; apps/web/app/(dashboard)/settings/company/page.tsx
IAM-026 | Tasks Schema | Create tasks table | Critical | 5 | Todo | Create tasks/work_orders table with status, assigned_to, notes. | Migration applies; status constrained; tenant_id indexed | Database | 2026-05-28 | Sprint 4 | 1 | 2026-05-28 | IAM-014 | supabase/migrations/026_tasks.sql
IAM-027 | Tasks Schema | Create task status history table | High | 3 | Todo | Store status changes for audit/timeline. | Every status change can be recorded; user and timestamp stored | Database | 2026-05-28 | Sprint 4 | 1 | 2026-05-28 | IAM-026 | supabase/migrations/027_task_status_history.sql
IAM-028 | Tasks API | Create task DTOs | High | 3 | Todo | Define create/update/status DTOs with validation. | DTO validation rejects bad status or missing required fields | Backend | 2026-05-29 | Sprint 4 | 1 | 2026-05-29 | IAM-026 | apps/api/src/modules/tasks/dto/create-task.dto.ts; update-task-status.dto.ts
IAM-029 | Tasks API | Build create task API | Critical | 8 | Todo | Transporter creates task/work order and assigns car puller. | Task created; assigned user must be in tenant; response includes task ID | Backend | 2026-05-29 | Sprint 4 | 2 | 2026-05-30 | IAM-018,IAM-026,IAM-028 | apps/api/src/modules/tasks/tasks.controller.ts; tasks.service.ts
IAM-030 | Tasks API | Build task listing API | Critical | 8 | Todo | Return tasks filtered by tenant and role. | Transporter sees tenant tasks; car puller sees assigned tasks only | Backend | 2026-05-30 | Sprint 4 | 2 | 2026-05-31 | IAM-029 | apps/api/src/modules/tasks/tasks.repository.ts
IAM-031 | Tasks API | Build task detail API | High | 5 | Todo | Return task, assignee, updates, history. | Only authorized tenant users can view; missing task returns 404 | Backend | 2026-05-31 | Sprint 4 | 2 | 2026-06-01 | IAM-030 | apps/api/src/modules/tasks/tasks.service.ts
IAM-032 | Tasks API | Build status transition API | Critical | 8 | Todo | Allow pending→accepted→in_progress→paused/completed→closed rules. | Invalid transitions rejected; history row created | Backend | 2026-06-01 | Sprint 4 | 2 | 2026-06-02 | IAM-027,IAM-031 | apps/api/src/modules/tasks/task-status.service.ts
IAM-033 | Tasks UI | Build task list page | High | 5 | Todo | Task board/list with status filters and priority badges. | Filters work; pagination/search works; tenant data only | Frontend | 2026-05-31 | Sprint 4 | 2 | 2026-06-01 | IAM-024,IAM-030 | apps/web/app/(dashboard)/tasks/page.tsx; components/tasks/TaskCard.tsx
IAM-034 | Tasks UI | Build create task page | High | 8 | Todo | Form for work order, notes, selected car puller, priority. | Form validates; task created; redirects to detail | Frontend | 2026-06-01 | Sprint 4 | 3 | 2026-06-03 | IAM-023,IAM-029 | apps/web/app/(dashboard)/tasks/new/page.tsx; components/tasks/CreateTaskForm.tsx
IAM-035 | Tasks UI | Build task detail page | High | 5 | Todo | Show task info, status, assignment, and timeline placeholder. | Task detail loads; status actions visible by role | Frontend | 2026-06-03 | Sprint 4 | 2 | 2026-06-04 | IAM-031,IAM-033 | apps/web/app/(dashboard)/tasks/[id]/page.tsx; components/tasks/TaskDetail.tsx
IAM-036 | Storage | Create storage buckets and policies | Critical | 5 | Todo | Configure work-orders, task-media, profile-images buckets. | Bucket policies isolate tenant paths; size/type rules documented | Database | 2026-06-05 | Sprint 5 | 1 | 2026-06-05 | IAM-014 | supabase/storage policies; supabase/migrations/036_storage.sql
IAM-037 | Uploads API | Build signed upload URL API | High | 8 | Todo | Backend returns signed upload URL for tenant-scoped object path. | Only authorized files allowed; path includes tenant_id | Backend | 2026-06-05 | Sprint 5 | 2 | 2026-06-06 | IAM-036,IAM-018 | apps/api/src/modules/uploads/uploads.controller.ts; uploads.service.ts
IAM-038 | Uploads API | Build file metadata table/API | High | 5 | Todo | Store file metadata linked to task/user. | File metadata created; ownership tracked; RLS enabled | Backend | 2026-06-06 | Sprint 5 | 2 | 2026-06-07 | IAM-037 | supabase/migrations/038_files.sql; apps/api/src/modules/uploads/file-metadata.service.ts
IAM-039 | Uploads UI | Build reusable upload component | High | 8 | Todo | Drag/drop or button upload with progress and validation. | PDF/image/video upload; progress bar; errors visible | Frontend | 2026-06-07 | Sprint 5 | 2 | 2026-06-08 | IAM-037 | apps/web/components/uploads/FileUploader.tsx
IAM-040 | Task Updates | Create task updates table | Critical | 3 | Todo | Support note/image/video update records by task. | Updates linked to task/tenant/user; timestamp stored | Database | 2026-06-07 | Sprint 5 | 1 | 2026-06-07 | IAM-026,IAM-038 | supabase/migrations/040_task_updates.sql
IAM-041 | Task Updates | Build create task update API | High | 8 | Todo | Car puller/transporter can add notes or media updates. | Update saved; linked files validated; unauthorized blocked | Backend | 2026-06-08 | Sprint 5 | 2 | 2026-06-09 | IAM-040 | apps/api/src/modules/task-updates/task-updates.controller.ts; service.ts
IAM-042 | Task Updates | Build task timeline UI | High | 8 | Todo | Display notes, photos, videos, status history in chronological feed. | Timeline sorted; media preview; user names visible | Frontend | 2026-06-09 | Sprint 5 | 3 | 2026-06-11 | IAM-035,IAM-039,IAM-041 | apps/web/components/tasks/TaskTimeline.tsx; TaskUpdateComposer.tsx
IAM-043 | Task Updates | Build car puller execution screen | Critical | 8 | Todo | Mobile-first accept/start/pause/complete with upload proof. | Large buttons; works on phone; status rules enforced | Frontend | 2026-06-10 | Sprint 5 | 3 | 2026-06-12 | IAM-032,IAM-042 | apps/web/app/(dashboard)/my-tasks/[id]/page.tsx
IAM-044 | Notifications | Create notifications table | High | 3 | Todo | Persist notifications by tenant/user/type/read state. | Unread count queryable; RLS enabled | Database | 2026-06-13 | Sprint 6 | 1 | 2026-06-13 | IAM-014 | supabase/migrations/044_notifications.sql
IAM-045 | Notifications | Build notification service | High | 5 | Todo | Generate notifications for assigned/accepted/completed updates. | Notifications created on task events; duplicate spam avoided | Backend | 2026-06-14 | Sprint 6 | 2 | 2026-06-15 | IAM-032,IAM-044 | apps/api/src/modules/notifications/notifications.service.ts
IAM-046 | Notifications | Build notifications API | Medium | 3 | Todo | List and mark notifications read. | Unread/read works; users see only their notifications | Backend | 2026-06-15 | Sprint 6 | 1 | 2026-06-15 | IAM-045 | apps/api/src/modules/notifications/notifications.controller.ts
IAM-047 | Notifications | Build notification dropdown UI | Medium | 5 | Todo | Topbar notification bell with unread badge. | Badge count correct; mark read works | Frontend | 2026-06-16 | Sprint 6 | 2 | 2026-06-17 | IAM-024,IAM-046 | apps/web/components/notifications/NotificationBell.tsx
IAM-048 | Dashboard | Build transporter dashboard | High | 5 | Todo | Cards for active/completed/pending tasks and recent updates. | KPIs accurate; recent task list links to detail | Frontend | 2026-06-15 | Sprint 6 | 2 | 2026-06-16 | IAM-030,IAM-042 | apps/web/app/(dashboard)/page.tsx; components/dashboard/KpiCard.tsx
IAM-049 | Dashboard | Build car puller dashboard | High | 5 | Todo | My pending/active/completed tasks with quick actions. | Assigned tasks only; action buttons work | Frontend | 2026-06-16 | Sprint 6 | 2 | 2026-06-17 | IAM-043 | apps/web/app/(dashboard)/my-tasks/page.tsx
IAM-050 | Search & Filters | Implement task search/filter API | Medium | 5 | Todo | Search by task ID, company, car puller, status, date range. | Filters combine correctly; pagination still works | Backend | 2026-06-17 | Sprint 6 | 2 | 2026-06-18 | IAM-030 | apps/api/src/modules/tasks/task-query.dto.ts
IAM-051 | Search & Filters | Implement frontend filters | Medium | 3 | Todo | Add task status/search/date filters to task list. | Filters update list; clear filters works | Frontend | 2026-06-18 | Sprint 6 | 1 | 2026-06-18 | IAM-050,IAM-033 | apps/web/components/tasks/TaskFilters.tsx
IAM-052 | Audit | Apply audit triggers to all tables | High | 5 | Todo | Ensure created_by/updated_by/created_at/updated_at across schema. | All core tables audited; timestamptz used; tests pass | Database | 2026-06-20 | Sprint 7 | 2 | 2026-06-21 | IAM-007,IAM-040,IAM-044 | supabase/migrations/052_apply_audit.sql
IAM-053 | Audit | Create audit logs table | Medium | 5 | Todo | Record sensitive business events and changes. | Audit logs created for task close/profile changes/invites | Database | 2026-06-21 | Sprint 7 | 2 | 2026-06-22 | IAM-052 | supabase/migrations/053_audit_logs.sql
IAM-054 | Security | Security hardening review | Critical | 8 | Todo | Review RLS, role guards, file policies, input validation. | No known cross-tenant access; checklist completed | Security | 2026-06-22 | Sprint 7 | 2 | 2026-06-23 | IAM-014,IAM-018,IAM-036,IAM-052 | security/checklists/tenant-security.md
IAM-055 | Testing | Backend unit tests for auth/tenant | High | 8 | Todo | Test register/login/tenant isolation guards. | Tests pass in CI; critical auth paths covered | QA | 2026-06-23 | Sprint 7 | 2 | 2026-06-24 | IAM-016,IAM-018 | apps/api/test/auth.spec.ts; tenants.spec.ts
IAM-056 | Testing | Backend tests for tasks/uploads | High | 8 | Todo | Test task CRUD/status/upload metadata. | Status transitions and upload validation covered | QA | 2026-06-24 | Sprint 7 | 2 | 2026-06-25 | IAM-032,IAM-041 | apps/api/test/tasks.spec.ts; uploads.spec.ts
IAM-057 | Testing | Frontend component tests | Medium | 5 | Todo | Test login, create task, task detail, upload component. | Critical components covered; tests pass | QA | 2026-06-25 | Sprint 7 | 2 | 2026-06-26 | IAM-039,IAM-042 | apps/web/__tests__/*
IAM-058 | Testing | End-to-end MVP flow test | High | 8 | Todo | Test transporter creates task and car puller completes it. | E2E passes; screenshots/videos generated if failing | QA | 2026-06-26 | Sprint 7 | 2 | 2026-06-27 | IAM-043,IAM-048,IAM-049 | e2e/iamonit-mvp.spec.ts
IAM-059 | Deployment | Setup GitHub Actions CI | High | 5 | Todo | Lint/test/build frontend and backend on PR. | CI passes; failed tests block merge | DevOps | 2026-06-28 | Sprint 8 | 2 | 2026-06-29 | IAM-055,IAM-057 | /.github/workflows/ci.yml
IAM-060 | Deployment | Deploy frontend to Vercel | High | 3 | Todo | Connect frontend repo, env vars, preview deployments. | Production URL live; preview deploys work | DevOps | 2026-06-29 | Sprint 8 | 1 | 2026-06-29 | IAM-059 | vercel.json; frontend env
IAM-061 | Deployment | Deploy backend API | High | 5 | Todo | Deploy NestJS API to Railway/Render/EC2. | API URL live; health endpoint OK; env vars secure | DevOps | 2026-06-29 | Sprint 8 | 2 | 2026-06-30 | IAM-059 | apps/api/Dockerfile; railway.json/render.yaml
IAM-062 | Deployment | Configure production Supabase | Critical | 5 | Todo | Apply migrations, storage policies, RLS in production. | Prod DB ready; backups enabled; policies verified | DevOps | 2026-06-30 | Sprint 8 | 2 | 2026-07-01 | IAM-054,IAM-061 | supabase migrations
IAM-063 | Deployment | Connect frontend to production API | High | 3 | Todo | Configure CORS, env variables, auth redirect URLs. | Frontend can login/register/create tasks in prod | DevOps | 2026-07-02 | Sprint 8 | 1 | 2026-07-02 | IAM-060,IAM-061,IAM-062 | frontend env; backend CORS config
IAM-064 | Release | Create MVP release checklist | High | 3 | Todo | Prepare go-live checklist and rollback plan. | Checklist complete; smoke tests signed off | Product | 2026-07-03 | Sprint 8 | 1 | 2026-07-03 | IAM-058,IAM-063 | release/mvp-checklist.md
IAM-065 | Release | User onboarding documentation | Medium | 3 | Todo | Create simple docs for transporter and car puller users. | Docs include screenshots and basic workflow | Product | 2026-07-03 | Sprint 8 | 2 | 2026-07-04 | IAM-064 | docs/user-guide.md
IAM-066 | Future Payments | Design payment model | Medium | 3 | Todo | Decide subscription/per-task/manual payment flow. | Payment decision documented; Stripe/manual options compared | Product | 2026-07-05 | Sprint 9 | 2 | 2026-07-06 | IAM-064 | docs/payments-design.md
IAM-067 | Future Payments | Create payments schema | Medium | 5 | Todo | Tables for payment status, amount, method, reference. | Schema supports manual paid/closed flow first | Database | 2026-07-07 | Sprint 9 | 2 | 2026-07-08 | IAM-066 | supabase/migrations/067_payments.sql
IAM-068 | Future Payments | Build payment confirmation UI | Medium | 5 | Todo | Transporter marks payment made and closes ticket. | Payment status visible; close action allowed after paid | Frontend | 2026-07-09 | Sprint 9 | 2 | 2026-07-10 | IAM-067,IAM-035 | apps/web/components/payments/PaymentPanel.tsx
IAM-069 | Real-Time | Add real-time task updates | Low | 8 | Todo | Use Supabase Realtime/WebSocket to refresh task timelines. | Task update appears without manual refresh | Fullstack | 2026-07-11 | Sprint 9 | 3 | 2026-07-13 | IAM-042,IAM-045 | apps/web/lib/realtime.ts; backend events
IAM-070 | Real-Time | Add live notification updates | Low | 5 | Todo | Unread notifications update in real-time. | Notification bell updates without refresh | Fullstack | 2026-07-12 | Sprint 9 | 2 | 2026-07-13 | IAM-047,IAM-069 | apps/web/components/notifications/NotificationBell.tsx
IAM-071 | Developer Automation | Establish Excel-driven Codex agent foundation | High | 3 | In Progress | Establish repository instructions, tracker rules, and the package location for an Excel-driven Codex task agent. | AGENTS.md contains the agent rules; Excel temporary files are ignored; the workbook contains IAM-071 and CODE-041; completed tasks are not selected again; no commits occur without a task ID. | DevOps | 2026-07-27 | Sprint 10 | 1 | 2026-07-27 | IAM-001,IAM-003 | AGENTS.md; .gitignore; planning/IAMONIT_Full_Project_Control_Workbook.xlsx | Every Git commit must begin with the exact related task ID.
IAM-072 | Developer Automation | Align tracker paths with workspace structure | High | 3 | Done | Align legacy backend and frontend file paths in the IAMONIT project tracker with the repository’s pnpm workspace structure. | Legacy backend paths use apps/api; legacy frontend paths use apps/web; canonical paths remain unchanged; no formulas, dropdowns, styles, or unrelated tracker content are damaged; remaining invalid path prefixes are reported. | DevOps | 2026-07-27 | Sprint 10 | 1 | 2026-07-27 | IAM-071 | planning/IAMONIT_Full_Project_Control_Workbook.xlsx | Normalize path-bearing tracker cells only. Do not change descriptive prose, URLs, package names, commands, class names, or task IDs.
IAM-073 | Developer Automation | Add controlled Codex execution pipeline | High | 5 | Done | Extend the IAMONIT task-agent so it can generate a task-specific Codex prompt and invoke Codex non-interactively under explicit safety controls. | The agent supports a non-mutating plan mode; execution requires an explicit flag; execution is blocked on a dirty working tree or protected branch; Codex runs only inside the repository workspace; results and exit status are captured; the workbook is never modified; no commit or push occurs automatically. | DevOps | 2026-07-27 | Sprint 10 | 2 | 2026-07-28 | IAM-071,IAM-072 | packages/task-agent/src/prompt-builder.ts; packages/task-agent/src/codex-executor.ts; packages/task-agent/src/git-preflight.ts; packages/task-agent/src/cli.ts | Plan mode is the default. Real execution requires explicit user action and must stop at human review.

## Sprint Board
Sprint | Task ID | Epic | Title | Owner | Priority | Points | Status | Dependencies | Acceptance Criteria
Sprint 1 | IAM-001 | Project Setup | Initialize Git repositories | DevOps | Critical | 3 | Done |  | Repos created; README exists; main/dev branches; .gitignore committed
Sprint 1 | IAM-002 | Project Setup | Create Next.js app | Frontend | Critical | 5 | Done | IAM-001 | apps/web/package.json exists; TypeScript is configured; App Router is configured; Tailwind CSS is configured; ESLint is configured; apps/web/app/layout.tsx exists; apps/web/app/page.tsx exists; the package participates in the existing pnpm workspace; the existing root dev:web command works with the web package; pnpm --filter <web-package> build passes
Sprint 1 | IAM-003 | Project Setup | Create NestJS backend | Backend | Critical | 5 | Done | IAM-001 | API starts locally; health endpoint returns OK; Swagger enabled
Sprint 1 | IAM-004 | Project Setup | Configure environment management | DevOps | High | 3 | Done | IAM-002,IAM-003 | No secrets committed; env schema validates required values
Sprint 1 | IAM-005 | Project Setup | Setup code quality tools | DevOps | High | 3 | Todo | IAM-002,IAM-003 | npm run lint passes; consistent formatting
Sprint 1 | IAM-006 | Database Foundation | Create Supabase project | Database | Critical | 3 | Done | IAM-004 | DB reachable; connection string configured; local migration flow documented
Sprint 1 | IAM-007 | Database Foundation | Create base audit trigger | Database | High | 5 | Done | IAM-006 | created_at/updated_at use timestamptz; trigger tested
Sprint 1 | IAM-008 | Auth | Build auth DTOs and validation | Backend | High | 3 | Done | IAM-003 | Invalid payloads rejected; password/email rules enforced
Sprint 1 | IAM-009 | Auth | Auth UI shell | Frontend | High | 5 | Done | IAM-002 | User can navigate between login/register; form validation visible
Sprint 2 | IAM-010 | Multi-Tenant Schema | Create tenants table | Database | Critical | 5 | Done | IAM-007 | Migration applies; tenant can be inserted; RLS enabled
Sprint 2 | IAM-011 | Multi-Tenant Schema | Create app_users table | Database | Critical | 5 | Done | IAM-010 | User profile linked to auth ID; role column constrained
Sprint 2 | IAM-012 | Multi-Tenant Schema | Create transporter profiles table | Database | High | 3 | Todo | IAM-010 | Profile belongs to tenant; audit fields exist
Sprint 2 | IAM-013 | Multi-Tenant Schema | Create car puller profiles table | Database | High | 3 | Todo | IAM-011 | Profile belongs to tenant/user; photo_url/logo_url supported
Sprint 2 | IAM-014 | Multi-Tenant Security | Implement tenant RLS policies | Security | Critical | 8 | Todo | IAM-010,IAM-011,IAM-012,IAM-013 | Tenant A cannot query Tenant B data; policy tests pass
Sprint 2 | IAM-015 | Auth | Implement register company flow | Backend | Critical | 8 | Todo | IAM-008,IAM-010,IAM-011 | New transporter creates tenant; first user becomes admin
Sprint 2 | IAM-016 | Auth | Implement login flow | Backend | Critical | 5 | Todo | IAM-008,IAM-011 | Valid login works; invalid login returns safe error; tenant_id included
Sprint 2 | IAM-017 | Frontend Auth | Connect login/register UI to API | Frontend | High | 5 | Todo | IAM-009,IAM-015,IAM-016 | Successful login redirects; errors displayed; loading states exist
Sprint 2 | IAM-018 | Authorization | Create auth guard and role guard | Backend | Critical | 5 | Todo | IAM-016 | Unauthorized blocked; forbidden roles blocked
Sprint 3 | IAM-019 | Tenant Invitations | Create invitations table | Database | High | 3 | Todo | IAM-014 | Tokens unique; accepted flag supported; RLS enabled
Sprint 3 | IAM-020 | Tenant Invitations | Build invite user API | Backend | High | 5 | Todo | IAM-018,IAM-019 | Invite created; duplicate invite handled; admin only
Sprint 3 | IAM-021 | Tenant Invitations | Build accept invitation API | Backend | High | 5 | Todo | IAM-020 | Valid token assigns tenant; expired token rejected
Sprint 3 | IAM-022 | User Management | Build users list API | Backend | High | 3 | Todo | IAM-018 | Only tenant users returned; pagination exists
Sprint 3 | IAM-023 | User Management | Build user management UI | Frontend | Medium | 5 | Todo | IAM-017,IAM-020,IAM-022 | Admin sees users; invite modal works; validation shown
Sprint 3 | IAM-024 | Layout | Create dashboard layout | Frontend | High | 5 | Todo | IAM-017 | Mobile and desktop usable; navigation links work
Sprint 3 | IAM-025 | Profile | Build transporter profile API/UI | Fullstack | Medium | 5 | Todo | IAM-012,IAM-018,IAM-024 | Profile saves; audit fields update; tenant isolated
Sprint 4 | IAM-026 | Tasks Schema | Create tasks table | Database | Critical | 5 | Todo | IAM-014 | Migration applies; status constrained; tenant_id indexed
Sprint 4 | IAM-027 | Tasks Schema | Create task status history table | Database | High | 3 | Todo | IAM-026 | Every status change can be recorded; user and timestamp stored
Sprint 4 | IAM-028 | Tasks API | Create task DTOs | Backend | High | 3 | Todo | IAM-026 | DTO validation rejects bad status or missing required fields
Sprint 4 | IAM-029 | Tasks API | Build create task API | Backend | Critical | 8 | Todo | IAM-018,IAM-026,IAM-028 | Task created; assigned user must be in tenant; response includes task ID
Sprint 4 | IAM-030 | Tasks API | Build task listing API | Backend | Critical | 8 | Todo | IAM-029 | Transporter sees tenant tasks; car puller sees assigned tasks only
Sprint 4 | IAM-031 | Tasks API | Build task detail API | Backend | High | 5 | Todo | IAM-030 | Only authorized tenant users can view; missing task returns 404
Sprint 4 | IAM-032 | Tasks API | Build status transition API | Backend | Critical | 8 | Todo | IAM-027,IAM-031 | Invalid transitions rejected; history row created
Sprint 4 | IAM-033 | Tasks UI | Build task list page | Frontend | High | 5 | Todo | IAM-024,IAM-030 | Filters work; pagination/search works; tenant data only
Sprint 4 | IAM-034 | Tasks UI | Build create task page | Frontend | High | 8 | Todo | IAM-023,IAM-029 | Form validates; task created; redirects to detail
Sprint 4 | IAM-035 | Tasks UI | Build task detail page | Frontend | High | 5 | Todo | IAM-031,IAM-033 | Task detail loads; status actions visible by role
Sprint 5 | IAM-036 | Storage | Create storage buckets and policies | Database | Critical | 5 | Todo | IAM-014 | Bucket policies isolate tenant paths; size/type rules documented
Sprint 5 | IAM-037 | Uploads API | Build signed upload URL API | Backend | High | 8 | Todo | IAM-036,IAM-018 | Only authorized files allowed; path includes tenant_id
Sprint 5 | IAM-038 | Uploads API | Build file metadata table/API | Backend | High | 5 | Todo | IAM-037 | File metadata created; ownership tracked; RLS enabled
Sprint 5 | IAM-039 | Uploads UI | Build reusable upload component | Frontend | High | 8 | Todo | IAM-037 | PDF/image/video upload; progress bar; errors visible
Sprint 5 | IAM-040 | Task Updates | Create task updates table | Database | Critical | 3 | Todo | IAM-026,IAM-038 | Updates linked to task/tenant/user; timestamp stored
Sprint 5 | IAM-041 | Task Updates | Build create task update API | Backend | High | 8 | Todo | IAM-040 | Update saved; linked files validated; unauthorized blocked
Sprint 5 | IAM-042 | Task Updates | Build task timeline UI | Frontend | High | 8 | Todo | IAM-035,IAM-039,IAM-041 | Timeline sorted; media preview; user names visible
Sprint 5 | IAM-043 | Task Updates | Build car puller execution screen | Frontend | Critical | 8 | Todo | IAM-032,IAM-042 | Large buttons; works on phone; status rules enforced
Sprint 6 | IAM-044 | Notifications | Create notifications table | Database | High | 3 | Todo | IAM-014 | Unread count queryable; RLS enabled
Sprint 6 | IAM-045 | Notifications | Build notification service | Backend | High | 5 | Todo | IAM-032,IAM-044 | Notifications created on task events; duplicate spam avoided
Sprint 6 | IAM-046 | Notifications | Build notifications API | Backend | Medium | 3 | Todo | IAM-045 | Unread/read works; users see only their notifications
Sprint 6 | IAM-047 | Notifications | Build notification dropdown UI | Frontend | Medium | 5 | Todo | IAM-024,IAM-046 | Badge count correct; mark read works
Sprint 6 | IAM-048 | Dashboard | Build transporter dashboard | Frontend | High | 5 | Todo | IAM-030,IAM-042 | KPIs accurate; recent task list links to detail
Sprint 6 | IAM-049 | Dashboard | Build car puller dashboard | Frontend | High | 5 | Todo | IAM-043 | Assigned tasks only; action buttons work
Sprint 6 | IAM-050 | Search & Filters | Implement task search/filter API | Backend | Medium | 5 | Todo | IAM-030 | Filters combine correctly; pagination still works
Sprint 6 | IAM-051 | Search & Filters | Implement frontend filters | Frontend | Medium | 3 | Todo | IAM-050,IAM-033 | Filters update list; clear filters works
Sprint 7 | IAM-052 | Audit | Apply audit triggers to all tables | Database | High | 5 | Todo | IAM-007,IAM-040,IAM-044 | All core tables audited; timestamptz used; tests pass
Sprint 7 | IAM-053 | Audit | Create audit logs table | Database | Medium | 5 | Todo | IAM-052 | Audit logs created for task close/profile changes/invites
Sprint 7 | IAM-054 | Security | Security hardening review | Security | Critical | 8 | Todo | IAM-014,IAM-018,IAM-036,IAM-052 | No known cross-tenant access; checklist completed
Sprint 7 | IAM-055 | Testing | Backend unit tests for auth/tenant | QA | High | 8 | Todo | IAM-016,IAM-018 | Tests pass in CI; critical auth paths covered
Sprint 7 | IAM-056 | Testing | Backend tests for tasks/uploads | QA | High | 8 | Todo | IAM-032,IAM-041 | Status transitions and upload validation covered
Sprint 7 | IAM-057 | Testing | Frontend component tests | QA | Medium | 5 | Todo | IAM-039,IAM-042 | Critical components covered; tests pass
Sprint 7 | IAM-058 | Testing | End-to-end MVP flow test | QA | High | 8 | Todo | IAM-043,IAM-048,IAM-049 | E2E passes; screenshots/videos generated if failing
Sprint 8 | IAM-059 | Deployment | Setup GitHub Actions CI | DevOps | High | 5 | Todo | IAM-055,IAM-057 | CI passes; failed tests block merge
Sprint 8 | IAM-060 | Deployment | Deploy frontend to Vercel | DevOps | High | 3 | Todo | IAM-059 | Production URL live; preview deploys work
Sprint 8 | IAM-061 | Deployment | Deploy backend API | DevOps | High | 5 | Todo | IAM-059 | API URL live; health endpoint OK; env vars secure
Sprint 8 | IAM-062 | Deployment | Configure production Supabase | DevOps | Critical | 5 | Todo | IAM-054,IAM-061 | Prod DB ready; backups enabled; policies verified
Sprint 8 | IAM-063 | Deployment | Connect frontend to production API | DevOps | High | 3 | Todo | IAM-060,IAM-061,IAM-062 | Frontend can login/register/create tasks in prod
Sprint 8 | IAM-064 | Release | Create MVP release checklist | Product | High | 3 | Todo | IAM-058,IAM-063 | Checklist complete; smoke tests signed off
Sprint 8 | IAM-065 | Release | User onboarding documentation | Product | Medium | 3 | Todo | IAM-064 | Docs include screenshots and basic workflow
Sprint 9 | IAM-066 | Future Payments | Design payment model | Product | Medium | 3 | Todo | IAM-064 | Payment decision documented; Stripe/manual options compared
Sprint 9 | IAM-067 | Future Payments | Create payments schema | Database | Medium | 5 | Todo | IAM-066 | Schema supports manual paid/closed flow first
Sprint 9 | IAM-068 | Future Payments | Build payment confirmation UI | Frontend | Medium | 5 | Todo | IAM-067,IAM-035 | Payment status visible; close action allowed after paid
Sprint 9 | IAM-069 | Real-Time | Add real-time task updates | Fullstack | Low | 8 | Todo | IAM-042,IAM-045 | Task update appears without manual refresh
Sprint 9 | IAM-070 | Real-Time | Add live notification updates | Fullstack | Low | 5 | Todo | IAM-047,IAM-069 | Notification bell updates without refresh
Sprint 10 | IAM-071 | Developer Automation | Establish Excel-driven Codex agent foundation | DevOps | High | 3 | In Progress | IAM-001,IAM-003 | Repository and workbook rules for the Excel-driven Codex agent are established.
Sprint 10 | IAM-072 | Developer Automation | Align tracker paths with workspace structure | DevOps | High | 3 | Done | IAM-071 | Tracker file paths match the actual apps/api and apps/web workspace structure.
Sprint 10 | IAM-073 | Developer Automation | Add controlled Codex execution pipeline | DevOps | High | 5 | Done | IAM-071,IAM-072 | The task-agent can safely prepare and explicitly launch one Codex coding task without committing, pushing, or updating the workbook.

## Timeline + Gantt
Task ID | Title | Sprint | Start | End | Duration | Status | Dependencies | 05/11 | 05/12 | 05/13 | 05/14 | 05/15 | 05/16 | 05/17 | 05/18 | 05/19 | 05/20 | 05/21 | 05/22 | 05/23 | 05/24 | 05/25 | 05/26 | 05/27 | 05/28 | 05/29 | 05/30 | 05/31 | 06/01 | 06/02 | 06/03 | 06/04 | 06/05 | 06/06 | 06/07 | 06/08 | 06/09 | 06/10 | 06/11 | 06/12 | 06/13 | 06/14 | 06/15 | 06/16 | 06/17 | 06/18 | 06/19 | 06/20 | 06/21
IAM-001 | Initialize Git repositories | Sprint 1 | 2026-05-11 | 2026-05-11 | 1 | Todo | bar: 05/11
IAM-002 | Create Next.js app | Sprint 1 | 2026-05-11 | 2026-05-12 | 2 | Todo | IAM-001 | bar: 05/11 to 05/12
IAM-003 | Create NestJS backend | Sprint 1 | 2026-05-11 | 2026-05-12 | 2 | Todo | IAM-001 | bar: 05/11 to 05/12
IAM-004 | Configure environment management | Sprint 1 | 2026-05-12 | 2026-05-12 | 1 | Todo | IAM-002,IAM-003 | bar: 05/12
IAM-005 | Setup code quality tools | Sprint 1 | 2026-05-12 | 2026-05-12 | 1 | Todo | IAM-002,IAM-003 | bar: 05/12
IAM-006 | Create Supabase project | Sprint 1 | 2026-05-13 | 2026-05-13 | 1 | Todo | IAM-004 | bar: 05/13
IAM-007 | Create base audit trigger | Sprint 1 | 2026-05-13 | 2026-05-14 | 2 | Todo | IAM-006 | bar: 05/13 to 05/14
IAM-008 | Build auth DTOs and validation | Sprint 1 | 2026-05-14 | 2026-05-14 | 1 | Todo | IAM-003 | bar: 05/14
IAM-009 | Auth UI shell | Sprint 1 | 2026-05-14 | 2026-05-15 | 2 | Todo | IAM-002 | bar: 05/14 to 05/15
IAM-010 | Create tenants table | Sprint 2 | 2026-05-16 | 2026-05-16 | 1 | Todo | IAM-007 | bar: 05/16
IAM-011 | Create app_users table | Sprint 2 | 2026-05-16 | 2026-05-16 | 1 | Todo | IAM-010 | bar: 05/16
IAM-012 | Create transporter profiles table | Sprint 2 | 2026-05-17 | 2026-05-17 | 1 | Todo | IAM-010 | bar: 05/17
IAM-013 | Create car puller profiles table | Sprint 2 | 2026-05-17 | 2026-05-17 | 1 | Todo | IAM-011 | bar: 05/17
IAM-014 | Implement tenant RLS policies | Sprint 2 | 2026-05-18 | 2026-05-19 | 2 | Todo | IAM-010,IAM-011,IAM-012,IAM-013 | bar: 05/18 to 05/19
IAM-015 | Implement register company flow | Sprint 2 | 2026-05-18 | 2026-05-19 | 2 | Todo | IAM-008,IAM-010,IAM-011 | bar: 05/18 to 05/19
IAM-016 | Implement login flow | Sprint 2 | 2026-05-19 | 2026-05-20 | 2 | Todo | IAM-008,IAM-011 | bar: 05/19 to 05/20
IAM-017 | Connect login/register UI to API | Sprint 2 | 2026-05-20 | 2026-05-21 | 2 | Todo | IAM-009,IAM-015,IAM-016 | bar: 05/20 to 05/21
IAM-018 | Create auth guard and role guard | Sprint 2 | 2026-05-20 | 2026-05-21 | 2 | Todo | IAM-016 | bar: 05/20 to 05/21
IAM-019 | Create invitations table | Sprint 3 | 2026-05-22 | 2026-05-22 | 1 | Todo | IAM-014 | bar: 05/22
IAM-020 | Build invite user API | Sprint 3 | 2026-05-22 | 2026-05-23 | 2 | Todo | IAM-018,IAM-019 | bar: 05/22 to 05/23
IAM-021 | Build accept invitation API | Sprint 3 | 2026-05-23 | 2026-05-24 | 2 | Todo | IAM-020 | bar: 05/23 to 05/24
IAM-022 | Build users list API | Sprint 3 | 2026-05-24 | 2026-05-24 | 1 | Todo | IAM-018 | bar: 05/24
IAM-023 | Build user management UI | Sprint 3 | 2026-05-25 | 2026-05-26 | 2 | Todo | IAM-017,IAM-020,IAM-022 | bar: 05/25 to 05/26
IAM-024 | Create dashboard layout | Sprint 3 | 2026-05-24 | 2026-05-25 | 2 | Todo | IAM-017 | bar: 05/24 to 05/25
IAM-025 | Build transporter profile API/UI | Sprint 3 | 2026-05-26 | 2026-05-27 | 2 | Todo | IAM-012,IAM-018,IAM-024 | bar: 05/26 to 05/27
IAM-026 | Create tasks table | Sprint 4 | 2026-05-28 | 2026-05-28 | 1 | Todo | IAM-014 | bar: 05/28
IAM-027 | Create task status history table | Sprint 4 | 2026-05-28 | 2026-05-28 | 1 | Todo | IAM-026 | bar: 05/28
IAM-028 | Create task DTOs | Sprint 4 | 2026-05-29 | 2026-05-29 | 1 | Todo | IAM-026 | bar: 05/29
IAM-029 | Build create task API | Sprint 4 | 2026-05-29 | 2026-05-30 | 2 | Todo | IAM-018,IAM-026,IAM-028 | bar: 05/29 to 05/30
IAM-030 | Build task listing API | Sprint 4 | 2026-05-30 | 2026-05-31 | 2 | Todo | IAM-029 | bar: 05/30 to 05/31
IAM-031 | Build task detail API | Sprint 4 | 2026-05-31 | 2026-06-01 | 2 | Todo | IAM-030 | bar: 05/31 to 06/01
IAM-032 | Build status transition API | Sprint 4 | 2026-06-01 | 2026-06-02 | 2 | Todo | IAM-027,IAM-031 | bar: 06/01 to 06/02
IAM-033 | Build task list page | Sprint 4 | 2026-05-31 | 2026-06-01 | 2 | Todo | IAM-024,IAM-030 | bar: 05/31 to 06/01
IAM-034 | Build create task page | Sprint 4 | 2026-06-01 | 2026-06-03 | 3 | Todo | IAM-023,IAM-029 | bar: 06/01 to 06/03
IAM-035 | Build task detail page | Sprint 4 | 2026-06-03 | 2026-06-04 | 2 | Todo | IAM-031,IAM-033 | bar: 06/03 to 06/04
IAM-036 | Create storage buckets and policies | Sprint 5 | 2026-06-05 | 2026-06-05 | 1 | Todo | IAM-014 | bar: 06/05
IAM-037 | Build signed upload URL API | Sprint 5 | 2026-06-05 | 2026-06-06 | 2 | Todo | IAM-036,IAM-018 | bar: 06/05 to 06/06
IAM-038 | Build file metadata table/API | Sprint 5 | 2026-06-06 | 2026-06-07 | 2 | Todo | IAM-037 | bar: 06/06 to 06/07
IAM-039 | Build reusable upload component | Sprint 5 | 2026-06-07 | 2026-06-08 | 2 | Todo | IAM-037 | bar: 06/07 to 06/08
IAM-040 | Create task updates table | Sprint 5 | 2026-06-07 | 2026-06-07 | 1 | Todo | IAM-026,IAM-038 | bar: 06/07
IAM-041 | Build create task update API | Sprint 5 | 2026-06-08 | 2026-06-09 | 2 | Todo | IAM-040 | bar: 06/08 to 06/09
IAM-042 | Build task timeline UI | Sprint 5 | 2026-06-09 | 2026-06-11 | 3 | Todo | IAM-035,IAM-039,IAM-041 | bar: 06/09 to 06/11
IAM-043 | Build car puller execution screen | Sprint 5 | 2026-06-10 | 2026-06-12 | 3 | Todo | IAM-032,IAM-042 | bar: 06/10 to 06/12
IAM-044 | Create notifications table | Sprint 6 | 2026-06-13 | 2026-06-13 | 1 | Todo | IAM-014 | bar: 06/13
IAM-045 | Build notification service | Sprint 6 | 2026-06-14 | 2026-06-15 | 2 | Todo | IAM-032,IAM-044 | bar: 06/14 to 06/15
IAM-046 | Build notifications API | Sprint 6 | 2026-06-15 | 2026-06-15 | 1 | Todo | IAM-045 | bar: 06/15
IAM-047 | Build notification dropdown UI | Sprint 6 | 2026-06-16 | 2026-06-17 | 2 | Todo | IAM-024,IAM-046 | bar: 06/16 to 06/17
IAM-048 | Build transporter dashboard | Sprint 6 | 2026-06-15 | 2026-06-16 | 2 | Todo | IAM-030,IAM-042 | bar: 06/15 to 06/16
IAM-049 | Build car puller dashboard | Sprint 6 | 2026-06-16 | 2026-06-17 | 2 | Todo | IAM-043 | bar: 06/16 to 06/17
IAM-050 | Implement task search/filter API | Sprint 6 | 2026-06-17 | 2026-06-18 | 2 | Todo | IAM-030 | bar: 06/17 to 06/18
IAM-051 | Implement frontend filters | Sprint 6 | 2026-06-18 | 2026-06-18 | 1 | Todo | IAM-050,IAM-033 | bar: 06/18
IAM-052 | Apply audit triggers to all tables | Sprint 7 | 2026-06-20 | 2026-06-21 | 2 | Todo | IAM-007,IAM-040,IAM-044 | bar: 06/20 to 06/21
IAM-053 | Create audit logs table | Sprint 7 | 2026-06-21 | 2026-06-22 | 2 | Todo | IAM-052 | bar: 06/21
IAM-054 | Security hardening review | Sprint 7 | 2026-06-22 | 2026-06-23 | 2 | Todo | IAM-014,IAM-018,IAM-036,IAM-052
IAM-055 | Backend unit tests for auth/tenant | Sprint 7 | 2026-06-23 | 2026-06-24 | 2 | Todo | IAM-016,IAM-018
IAM-056 | Backend tests for tasks/uploads | Sprint 7 | 2026-06-24 | 2026-06-25 | 2 | Todo | IAM-032,IAM-041
IAM-057 | Frontend component tests | Sprint 7 | 2026-06-25 | 2026-06-26 | 2 | Todo | IAM-039,IAM-042
IAM-058 | End-to-end MVP flow test | Sprint 7 | 2026-06-26 | 2026-06-27 | 2 | Todo | IAM-043,IAM-048,IAM-049
IAM-059 | Setup GitHub Actions CI | Sprint 8 | 2026-06-28 | 2026-06-29 | 2 | Todo | IAM-055,IAM-057
IAM-060 | Deploy frontend to Vercel | Sprint 8 | 2026-06-29 | 2026-06-29 | 1 | Todo | IAM-059
IAM-061 | Deploy backend API | Sprint 8 | 2026-06-29 | 2026-06-30 | 2 | Todo | IAM-059
IAM-062 | Configure production Supabase | Sprint 8 | 2026-06-30 | 2026-07-01 | 2 | Todo | IAM-054,IAM-061
IAM-063 | Connect frontend to production API | Sprint 8 | 2026-07-02 | 2026-07-02 | 1 | Todo | IAM-060,IAM-061,IAM-062
IAM-064 | Create MVP release checklist | Sprint 8 | 2026-07-03 | 2026-07-03 | 1 | Todo | IAM-058,IAM-063
IAM-065 | User onboarding documentation | Sprint 8 | 2026-07-03 | 2026-07-04 | 2 | Todo | IAM-064
IAM-066 | Design payment model | Sprint 9 | 2026-07-05 | 2026-07-06 | 2 | Todo | IAM-064
IAM-067 | Create payments schema | Sprint 9 | 2026-07-07 | 2026-07-08 | 2 | Todo | IAM-066
IAM-068 | Build payment confirmation UI | Sprint 9 | 2026-07-09 | 2026-07-10 | 2 | Todo | IAM-067,IAM-035
IAM-069 | Add real-time task updates | Sprint 9 | 2026-07-11 | 2026-07-13 | 3 | Todo | IAM-042,IAM-045
IAM-070 | Add live notification updates | Sprint 9 | 2026-07-12 | 2026-07-13 | 2 | Todo | IAM-047,IAM-069

## Dependencies
Task ID | Task Title | Depends On | Dependency Meaning | Blocking Risk | Ready?
IAM-001 | Initialize Git repositories |  | No dependency | Low | Done
IAM-002 | Create Next.js app | IAM-001 | Finish dependency before starting this task | Medium | Done
IAM-003 | Create NestJS backend | IAM-001 | Finish dependency before starting this task | Medium | Done
IAM-004 | Configure environment management | IAM-002,IAM-003 | Finish dependency before starting this task | Medium | Ready
IAM-005 | Setup code quality tools | IAM-002,IAM-003 | Finish dependency before starting this task | Medium | Ready
IAM-006 | Create Supabase project | IAM-004 | Finish dependency before starting this task | Medium | Ready
IAM-007 | Create base audit trigger | IAM-006 | Finish dependency before starting this task | Medium | Ready
IAM-008 | Build auth DTOs and validation | IAM-003 | Finish dependency before starting this task | Medium | Ready
IAM-009 | Auth UI shell | IAM-002 | Finish dependency before starting this task | Medium | Ready
IAM-010 | Create tenants table | IAM-007 | Finish dependency before starting this task | Medium | Ready
IAM-011 | Create app_users table | IAM-010 | Finish dependency before starting this task | Medium | Ready
IAM-012 | Create transporter profiles table | IAM-010 | Finish dependency before starting this task | Medium | Ready
IAM-013 | Create car puller profiles table | IAM-011 | Finish dependency before starting this task | Medium | Ready
IAM-014 | Implement tenant RLS policies | IAM-010,IAM-011,IAM-012,IAM-013 | Finish dependency before starting this task | Medium | Ready
IAM-015 | Implement register company flow | IAM-008,IAM-010,IAM-011 | Finish dependency before starting this task | Medium | Ready
IAM-016 | Implement login flow | IAM-008,IAM-011 | Finish dependency before starting this task | Medium | Ready
IAM-017 | Connect login/register UI to API | IAM-009,IAM-015,IAM-016 | Finish dependency before starting this task | Medium | Ready
IAM-018 | Create auth guard and role guard | IAM-016 | Finish dependency before starting this task | Medium | Ready
IAM-019 | Create invitations table | IAM-014 | Finish dependency before starting this task | Medium | Ready
IAM-020 | Build invite user API | IAM-018,IAM-019 | Finish dependency before starting this task | Medium | Ready
IAM-021 | Build accept invitation API | IAM-020 | Finish dependency before starting this task | Medium | Ready
IAM-022 | Build users list API | IAM-018 | Finish dependency before starting this task | Medium | Ready
IAM-023 | Build user management UI | IAM-017,IAM-020,IAM-022 | Finish dependency before starting this task | Medium | Ready
IAM-024 | Create dashboard layout | IAM-017 | Finish dependency before starting this task | Medium | Ready
IAM-025 | Build transporter profile API/UI | IAM-012,IAM-018,IAM-024 | Finish dependency before starting this task | Medium | Ready
IAM-026 | Create tasks table | IAM-014 | Finish dependency before starting this task | Medium | Ready
IAM-027 | Create task status history table | IAM-026 | Finish dependency before starting this task | Medium | Ready
IAM-028 | Create task DTOs | IAM-026 | Finish dependency before starting this task | Medium | Ready
IAM-029 | Build create task API | IAM-018,IAM-026,IAM-028 | Finish dependency before starting this task | Medium | Ready
IAM-030 | Build task listing API | IAM-029 | Finish dependency before starting this task | Medium | Ready
IAM-031 | Build task detail API | IAM-030 | Finish dependency before starting this task | Medium | Ready
IAM-032 | Build status transition API | IAM-027,IAM-031 | Finish dependency before starting this task | Medium | Ready
IAM-033 | Build task list page | IAM-024,IAM-030 | Finish dependency before starting this task | Medium | Ready
IAM-034 | Build create task page | IAM-023,IAM-029 | Finish dependency before starting this task | Medium | Ready
IAM-035 | Build task detail page | IAM-031,IAM-033 | Finish dependency before starting this task | Medium | Ready
IAM-036 | Create storage buckets and policies | IAM-014 | Finish dependency before starting this task | Medium | Ready
IAM-037 | Build signed upload URL API | IAM-036,IAM-018 | Finish dependency before starting this task | Medium | Ready
IAM-038 | Build file metadata table/API | IAM-037 | Finish dependency before starting this task | Medium | Ready
IAM-039 | Build reusable upload component | IAM-037 | Finish dependency before starting this task | Medium | Ready
IAM-040 | Create task updates table | IAM-026,IAM-038 | Finish dependency before starting this task | Medium | Ready
IAM-041 | Build create task update API | IAM-040 | Finish dependency before starting this task | Medium | Ready
IAM-042 | Build task timeline UI | IAM-035,IAM-039,IAM-041 | Finish dependency before starting this task | Medium | Ready
IAM-043 | Build car puller execution screen | IAM-032,IAM-042 | Finish dependency before starting this task | Medium | Ready
IAM-044 | Create notifications table | IAM-014 | Finish dependency before starting this task | Medium | Ready
IAM-045 | Build notification service | IAM-032,IAM-044 | Finish dependency before starting this task | Medium | Ready
IAM-046 | Build notifications API | IAM-045 | Finish dependency before starting this task | Medium | Ready
IAM-047 | Build notification dropdown UI | IAM-024,IAM-046 | Finish dependency before starting this task | Medium | Ready
IAM-048 | Build transporter dashboard | IAM-030,IAM-042 | Finish dependency before starting this task | Medium | Ready
IAM-049 | Build car puller dashboard | IAM-043 | Finish dependency before starting this task | Medium | Ready
IAM-050 | Implement task search/filter API | IAM-030 | Finish dependency before starting this task | Medium | Ready
IAM-051 | Implement frontend filters | IAM-050,IAM-033 | Finish dependency before starting this task | Medium | Ready
IAM-052 | Apply audit triggers to all tables | IAM-007,IAM-040,IAM-044 | Finish dependency before starting this task | Medium | Ready
IAM-053 | Create audit logs table | IAM-052 | Finish dependency before starting this task | Medium | Ready
IAM-054 | Security hardening review | IAM-014,IAM-018,IAM-036,IAM-052 | Finish dependency before starting this task | Medium | Ready
IAM-055 | Backend unit tests for auth/tenant | IAM-016,IAM-018 | Finish dependency before starting this task | Medium | Ready
IAM-056 | Backend tests for tasks/uploads | IAM-032,IAM-041 | Finish dependency before starting this task | Medium | Ready
IAM-057 | Frontend component tests | IAM-039,IAM-042 | Finish dependency before starting this task | Medium | Ready
IAM-058 | End-to-end MVP flow test | IAM-043,IAM-048,IAM-049 | Finish dependency before starting this task | Medium | Ready
IAM-059 | Setup GitHub Actions CI | IAM-055,IAM-057 | Finish dependency before starting this task | Medium | Ready
IAM-060 | Deploy frontend to Vercel | IAM-059 | Finish dependency before starting this task | Medium | Ready
IAM-061 | Deploy backend API | IAM-059 | Finish dependency before starting this task | Medium | Ready
IAM-062 | Configure production Supabase | IAM-054,IAM-061 | Finish dependency before starting this task | Medium | Ready
IAM-063 | Connect frontend to production API | IAM-060,IAM-061,IAM-062 | Finish dependency before starting this task | Medium | Ready
IAM-064 | Create MVP release checklist | IAM-058,IAM-063 | Finish dependency before starting this task | Medium | Ready
IAM-065 | User onboarding documentation | IAM-064 | Finish dependency before starting this task | Medium | Ready
IAM-066 | Design payment model | IAM-064 | Finish dependency before starting this task | Medium | Ready
IAM-067 | Create payments schema | IAM-066 | Finish dependency before starting this task | Medium | Ready
IAM-068 | Build payment confirmation UI | IAM-067,IAM-035 | Finish dependency before starting this task | Medium | Ready
IAM-069 | Add real-time task updates | IAM-042,IAM-045 | Finish dependency before starting this task | Medium | Ready
IAM-070 | Add live notification updates | IAM-047,IAM-069 | Finish dependency before starting this task | Medium | Ready

## IntelliJ Coding Tasks
Code | Layer | Module | File / Class | Exact Coding Task | Implementation Notes | Related Jira Task | Acceptance Criteria | Status
CODE-001 | Backend | config | apps/api/src/config/env.config.ts; apps/api/src/app.module.ts; apps/api/.env.example; apps/web/.env.example | Complete environment configuration and validation | Validate required API environment variables and fail clearly during startup when required values are missing or invalid. Keep configuration typed and centralized. Add repository-safe .env.example documentation for required API variables and add frontend public-environment examples or conventions where needed, using the appropriate NEXT_PUBLIC_ prefix for browser-exposed values. Do not add real credentials, tokens, passwords, URLs containing secrets, or production values. Do not provision Supabase or perform database migrations in this task. | IAM-004 | Required API environment values are validated; invalid or missing required values produce a clear startup failure; API and frontend example-environment files document required variables; no secrets are committed; existing development configuration continues to work; TypeScript, lint, and relevant tests pass. | Done
CODE-002 | Backend | auth | apps/api/src/modules/auth/dto/register.dto.ts | Create RegisterDto | Fields: email,password,role,companyName,fullName,phone. Use class-validator. | IAM-008 | Invalid registration payload rejected | Done
CODE-003 | Backend | auth | apps/api/src/modules/auth/dto/login.dto.ts | Create LoginDto | Fields: email,password. | IAM-008 | Invalid login payload rejected | Done
CODE-048 | Backend | auth / supabase | apps/api/src/common/supabase/supabase.constants.ts; apps/api/src/common/supabase/supabase.provider.ts; apps/api/src/common/supabase/supabase.module.ts; apps/api/src/common/supabase/supabase.provider.spec.ts; apps/api/src/modules/auth/auth.types.ts; apps/api/src/modules/auth/dto/auth-response.dto.ts; apps/api/src/modules/auth/dto/register.dto.ts; apps/api/src/modules/auth/auth.module.ts; apps/api/package.json; ././pnpm-lock.yaml | Create authentication integration foundation | Install and configure @supabase/supabase-js and pg for the NestJS API. Create separate injectable Supabase public and admin clients. The public client uses SUPABASE_URL and SUPABASE_ANON_KEY. The admin client uses SUPABASE_URL and SUPABASE_SERVICE_ROLE_KEY and must remain server-only. Read configuration only through ConfigService. Never return, log, serialize, or otherwise expose the service-role key. Define the approved authentication response contract: - session is either null or an object containing accessToken, refreshToken, expiresIn, expiresAt, and tokenType. - requiresEmailConfirmation is boolean. - user contains id, email, tenantId, role, fullName, and phone. Update RegisterDto so registration accepts only email, password, companyName, fullName, and phone. Remove the client-supplied role field. LoginDto remains email and password. Register the providers and authentication types through AuthModule. Add focused unit tests for provider construction, configuration validation, response mapping types, and secret boundaries. Do not implement registration orchestration, login behavior, controllers, database writes, JWT validation, guards, frontend changes, or hosted calls. | IAM-015,IAM-016 | The API package contains @supabase/supabase-js, pg, and required type dependencies. Injectable public and admin Supabase clients are available through Nest dependency injection. The public client uses only the anonymous key and the admin client uses the server-only service-role key. RegisterDto accepts email, password, companyName, fullName, and phone and no longer accepts role. Auth response DTOs represent the approved nullable-session, requiresEmailConfirmation, and user-context contract. Configuration is loaded through ConfigService. No secret value is printed, returned, committed, or exposed to frontend code. Unit tests pass. No Auth user, tenant, app-user, session, controller, RLS policy, frontend, or hosted-project operation is created. | Todo
CODE-005 | Backend | auth | apps/api/src/modules/auth/auth.service.ts; apps/api/src/modules/auth/auth.repository.ts; apps/api/src/modules/auth/auth.service.spec.ts; apps/api/src/modules/auth/auth.repository.spec.ts | Implement company registration orchestration | Implement the registration service using the injectable Supabase clients and a PostgreSQL repository backed by pg and DATABASE_URL. Accept RegisterDto containing email, password, companyName, fullName, and phone. Do not accept or trust a client-supplied role. Assign admin to the first user. Create the Supabase Auth identity through the public sign-up capability and respect the Supabase email-confirmation setting. Then create exactly one tenant and one app_users record in one PostgreSQL transaction. The app_users id equals the Supabase Auth user id and references the new tenant. If the database transaction fails after Auth creation, roll back all database writes and attempt compensating deletion of the Auth identity through the admin client. If compensation fails, log only the orphaned Auth user identifier and a safe internal error; never log keys, passwords, access tokens, refresh tokens, or provider response bodies. Return the approved auth response. When Supabase returns no session because email confirmation is required, return session null and requiresEmailConfirmation true. Map duplicate email or tenant name to 409, provider unavailability to 503, and unexpected or failed-compensation errors to 500. Do not create transporter_profiles, controllers, login behavior, guards, JWT strategy code, RLS policies, frontend code, or hosted operations. | IAM-015 | Successful registration creates exactly one Supabase Auth identity, one tenant, and one linked app_users row with role admin. Tenant and app-user writes occur in one PostgreSQL transaction. The returned response follows the approved session and user-context contract. When email confirmation is required, session is null and requiresEmailConfirmation is true. A database failure leaves no tenant or app_users records and triggers compensating Auth-user deletion. Tests cover successful registration, role derivation, duplicate email, duplicate company name, Auth failure, transaction rollback, successful compensation, failed compensation, confirmation-required responses, session responses, and secret-safe errors. No transporter profile, controller, login implementation, RLS policy, frontend file, hosted database, or hosted Auth operation is modified. | Todo
CODE-049 | Backend | auth | apps/api/src/modules/auth/auth.service.ts; apps/api/src/modules/auth/auth.repository.ts; apps/api/src/modules/auth/auth.service.spec.ts; apps/api/src/modules/auth/auth.repository.spec.ts | Implement login service and user context | Add login behavior to AuthService using the public Supabase client. Authenticate email and password through Supabase Auth. For a successful session, load the linked public.app_users record and return user context containing id, email, tenantId, role, fullName, and phone. Return the approved non-null session object containing accessToken, refreshToken, expiresIn, expiresAt, and tokenType, with requiresEmailConfirmation false. Map invalid credentials to 401. Map a valid Auth identity without a linked app_users profile to 403. Map Supabase availability errors to 503 and unexpected consistency failures to a safe 500. Never use or expose the service-role key for password authentication. Do not implement controllers, JWT strategy, guards, refresh endpoints, logout, frontend integration, RLS policies, or hosted operations. | IAM-016 | Valid credentials return a Supabase session and linked app-user context containing user id, email, tenant id, role, full name, and phone. Invalid credentials return 401 without revealing whether the email exists. A valid Auth identity without an app_users row returns 403. Provider unavailability returns 503. Unexpected failures return a safe 500. Tests cover valid login, invalid credentials, missing profile, session mapping, tenant and role context, provider failure, and absence of secrets in responses and logs. No controller, JWT strategy, guard, registration side effect, frontend file, RLS policy, hosted database, or hosted Auth project is modified. | Todo
CODE-004 | Backend | auth | apps/api/src/modules/auth/auth.controller.ts; apps/api/src/modules/auth/auth.controller.spec.ts | Implement register and login controllers | Implement thin NestJS controller endpoints backed only by AuthService. POST /auth/register accepts RegisterDto, delegates to AuthService.register, and returns the approved AuthResponseDto with HTTP 201. POST /auth/login accepts LoginDto, delegates to AuthService.login, and returns the approved AuthResponseDto with HTTP 200. The controller must not instantiate Supabase clients, access ConfigService, perform database queries, manage transactions, create JWTs, or expose provider errors. Preserve Nest DTO validation and service-level safe exception mappings. Do not modify services, repositories, Supabase providers, JWT strategy, guards, frontend files, RLS policies, or hosted resources. | IAM-015,IAM-016 | POST /auth/register returns HTTP 201 and the AuthService registration response. POST /auth/login returns HTTP 200 and the AuthService login response. Controller tests verify DTO delegation, status codes, response forwarding, and safe propagation of documented HTTP exceptions. The controller contains no Supabase, database, transaction, JWT-signing, or secret-handling logic. | Todo
CODE-006 | Backend | auth | apps/api/src/modules/auth/jwt.strategy.ts | Implement JWT strategy | Validate token, attach user_id, tenant_id, role. | IAM-016 | Protected requests have user context | Todo
CODE-007 | Backend | common | apps/api/src/common/guards/auth.guard.ts | Create auth guard | Reject unauthenticated requests. | IAM-018 | 401 returned without token | Todo
CODE-008 | Backend | common | apps/api/src/common/guards/roles.guard.ts | Create role guard | Allow decorators like @Roles("admin"). | IAM-018 | 403 returned for wrong role | Todo
CODE-009 | Backend | tenants | apps/api/src/modules/tenants/tenants.service.ts | Create tenant service | Create/get current tenant and update company settings. | IAM-025 | Tenant data isolated | Todo
CODE-010 | Backend | users | apps/api/src/modules/users/users.controller.ts | Build users controller | GET /users returns tenant users. | IAM-022 | No cross-tenant users returned | Todo
CODE-011 | Backend | users | apps/api/src/modules/users/users.service.ts | Build users service | Find users by tenant and update roles. | IAM-022 | Role changes restricted to admin | Todo
CODE-012 | Backend | invitations | apps/api/src/modules/invitations/invitations.controller.ts | Build invitation endpoints | POST /invitations and POST /invitations/accept. | IAM-020,IAM-021 | Invitation flow works | Todo
CODE-013 | Backend | invitations | apps/api/src/modules/invitations/invitations.service.ts | Implement token creation/acceptance | Generate secure token, handle expiry/accepted state. | IAM-020,IAM-021 | Expired tokens rejected | Todo
CODE-014 | Backend | tasks | apps/api/src/modules/tasks/dto/create-task.dto.ts | Create CreateTaskDto | Fields: assignedTo, notes, priority, workOrderFileId. | IAM-028 | Bad task payload rejected | Todo
CODE-015 | Backend | tasks | apps/api/src/modules/tasks/tasks.controller.ts | Implement task CRUD endpoints | GET /tasks, POST /tasks, GET /tasks/:id. | IAM-029,IAM-030,IAM-031 | CRUD works with tenant isolation | Todo
CODE-016 | Backend | tasks | apps/api/src/modules/tasks/tasks.service.ts | Implement task business logic | Create, list, get detail with role-based filtering. | IAM-029,IAM-030,IAM-031 | Car puller sees only assigned tasks | Todo
CODE-017 | Backend | tasks | apps/api/src/modules/tasks/task-status.service.ts | Implement status transitions | Validate pending→accepted→in_progress→paused/completed→closed. | IAM-032 | Invalid transition rejected | Todo
CODE-018 | Backend | uploads | apps/api/src/modules/uploads/uploads.controller.ts | Build signed URL endpoint | POST /uploads/signed-url. | IAM-037 | Returns signed upload URL | Todo
CODE-019 | Backend | uploads | apps/api/src/modules/uploads/uploads.service.ts | Generate tenant-scoped storage paths | Path format: tenant/{tenant_id}/tasks/{task_id}/file. | IAM-037 | Storage path cannot escape tenant | Todo
CODE-020 | Backend | task-updates | apps/api/src/modules/task-updates/task-updates.controller.ts | Build task update endpoint | POST /tasks/:id/updates. | IAM-041 | Can add note/media update | Todo
CODE-021 | Backend | notifications | apps/api/src/modules/notifications/notifications.service.ts | Emit notification records | Create notifications on assign/status/update. | IAM-045 | Notifications created reliably | Todo
CODE-022 | Frontend | auth | apps/web/app/(auth)/login/page.tsx | Build login page | Create the client-side login page UI shell with email and password fields, client-side validation, accessible labels, validation and error messages, loading/disabled-state presentation, and navigation to the registration page. Do not call the backend, store authentication state, create sessions, or redirect to the dashboard. Those behaviors belong to later integration tasks. | IAM-009 | Login page renders email and password fields; invalid input displays clear validation messages; loading and error presentation states are supported; the submit button has appropriate disabled behavior; and a registration navigation link is available. No backend request, authentication persistence, or dashboard redirect is implemented. | Done
CODE-023 | Frontend | auth | apps/web/app/(auth)/register/page.tsx | Build registration page | Create the client-side registration page UI shell with full name, company name, email, phone, password, required confirm-password, and role-selection fields. Require a minimum of 8 password characters and require password and confirm password to match. Include client-side validation, accessible labels and field-level errors, loading and disabled states, and navigation to /login. Do not call the backend, create an account, store authentication state, create a session or token, persist data, or redirect after submission. Those behaviors belong to later integration tasks. | IAM-009 | Registration page renders all required fields and role selection; password requires at least 8 characters; confirm password is required and must match password; invalid input displays accessible field-level validation errors; loading and error presentation states are supported; the submit button has appropriate disabled behavior; and navigation to /login is available. No backend call, account creation, session, token, authentication persistence, other persistence, or post-registration redirect is implemented. | Done
CODE-024 | Frontend | lib | apps/web/lib/api.ts | Create API client | Fetch wrapper with auth token and error handling. | IAM-017 | API errors handled consistently | Todo
CODE-025 | Frontend | lib | apps/web/lib/auth.ts | Create auth helpers | Login/logout/getSession/useCurrentUser. | IAM-017 | Session persists safely | Todo
CODE-026 | Frontend | layout | apps/web/components/layout/Sidebar.tsx | Build sidebar navigation | Role-based nav items. | IAM-024 | Car puller/admin see correct nav | Todo
CODE-027 | Frontend | layout | apps/web/components/layout/Topbar.tsx | Build topbar | Tenant name, user menu, notification bell. | IAM-024,IAM-047 | Topbar shows current context | Todo
CODE-028 | Frontend | tasks | apps/web/app/(dashboard)/tasks/page.tsx | Build task list page | Filters, search, cards/table. | IAM-033,IAM-051 | Task list usable | Todo
CODE-029 | Frontend | tasks | apps/web/app/(dashboard)/tasks/new/page.tsx | Build create task page | Form with assigned car puller, notes, work order upload. | IAM-034 | Task can be created | Todo
CODE-030 | Frontend | tasks | apps/web/app/(dashboard)/tasks/[id]/page.tsx | Build task detail page | Task status, notes, timeline, action buttons. | IAM-035 | Task details display | Todo
CODE-031 | Frontend | tasks | apps/web/components/tasks/TaskTimeline.tsx | Build timeline component | Show notes, photos, videos, status history. | IAM-042 | Timeline sorted correctly | Todo
CODE-032 | Frontend | uploads | apps/web/components/uploads/FileUploader.tsx | Build file uploader | Upload PDF/image/video using signed URL. | IAM-039 | Progress/errors shown | Todo
CODE-033 | Frontend | my-tasks | apps/web/app/(dashboard)/my-tasks/[id]/page.tsx | Build mobile execution page | Accept/start/pause/complete + proof upload. | IAM-043 | Usable on mobile | Todo
CODE-034 | Frontend | notifications | apps/web/components/notifications/NotificationBell.tsx | Build notification dropdown | Unread badge, list, mark read. | IAM-047 | Unread count updates | Todo
CODE-035 | Database | migrations | supabase/migrations/20260804165923_create_tenants.sql | Create tenants migration | Create one ordered Supabase PostgreSQL migration for public.tenants. Define id as uuid primary key with default gen_random_uuid(); define name as text, required, and unique; define status as text, required, with default 'active'; and define created_by and updated_by as nullable uuid columns without foreign keys at this stage. Follow the IAM-007 audit convention by defining created_at and updated_at as timestamptz NOT NULL DEFAULT now() and attach a BEFORE UPDATE trigger that executes public.set_updated_at(). Enable row-level security on public.tenants, but do not create tenant-access policies because policy implementation belongs to IAM-014. Do not create or depend on app_users, memberships, profiles, authentication endpoints, API code, or other application files. Apply and verify the migration only against the local Supabase database. Do not apply it to the hosted Supabase project. | IAM-010 | The timestamped migration supabase/migrations/20260804165923_create_tenants.sql creates public.tenants with id, name, status, created_at, updated_at, created_by, and updated_by. id is a uuid primary key with default gen_random_uuid(); name is required and unique; status is required and defaults to 'active'; created_by and updated_by are nullable uuid columns without foreign keys; created_at and updated_at use timestamptz NOT NULL DEFAULT now(). A BEFORE UPDATE trigger invokes public.set_updated_at(); row-level security is enabled without adding IAM-014 tenant-access policies; the migration applies successfully to the local Supabase database; a privileged local insert succeeds; a duplicate tenant name is rejected; updating a tenant changes updated_at; no app_users, memberships, profiles, API files, or unrelated tables are created; and no hosted-project migration is applied. | Done
CODE-036 | Database | migrations | supabase/migrations/026_tasks.sql | Create tasks migration | tasks table indexes tenant_id,status,assigned_to. | IAM-026 | Task queries performant | Todo
CODE-037 | Database | migrations | supabase/migrations/014_rls_core.sql | Create core RLS policies | Policies for tenants/users/profiles. | IAM-014 | Cross-tenant read blocked | Todo
CODE-038 | Database | migrations | supabase/migrations/036_storage.sql | Create storage policies | Tenant-scoped buckets and paths. | IAM-036 | Files isolated by tenant | Todo
CODE-039 | QA | tests | apps/api/test/tasks.spec.ts | Write task service tests | Create/list/status transition tests. | IAM-056 | Tests pass | Todo
CODE-040 | QA | e2e | e2e/iamonit-mvp.spec.ts | Write E2E MVP test | Register, create task, accept, upload proof, complete. | IAM-058 | E2E flow passes | Todo
CODE-041 | Tooling | task-agent | packages/task-agent/src/cli.ts | Create read-only workbook reader and eligible-task selector | Use ExcelJS to read the Backlog and IntelliJ Coding Tasks sheets. Skip Done, In Progress, Blocked, and Review tasks. Select a Todo task only when all dependencies are Done. Print one selected task and stop without changing the workbook or application code. | IAM-071 | The CLI identifies exactly one eligible task, respects dependencies, skips completed work, and makes no workbook changes. | Done
CODE-042 | Tooling | task-agent | packages/task-agent/src/path-normalizer.ts | Validate and normalize coding-task file paths | Add runtime path normalization and validation to the read-only task agent. Convert known legacy prefixes to canonical workspace paths, reject unsafe paths, preserve already canonical paths, and print both original and normalized task paths. | IAM-072 | backend paths normalize to apps/api; frontend paths normalize to apps/web; canonical paths remain unchanged; absolute paths and directory traversal are rejected; future files are allowed to be absent; tests cover valid, legacy, unsafe, and multiple-path inputs. | Done
CODE-043 | Tooling | task-agent | packages/task-agent/src/prompt-builder.ts; packages/task-agent/src/codex-executor.ts; packages/task-agent/src/git-preflight.ts; packages/task-agent/src/cli.ts | Build task prompt generation and controlled Codex execution | Generate a detailed prompt from the single selected workbook task. Keep plan mode as the default. Add an explicit execution mode that invokes codex exec using Node child_process.spawn without a shell. Pass the prompt through stdin. Use workspace-write sandboxing, disable network access, capture JSONL events and the final assistant message, verify a clean Git working tree, reject protected branches, preserve the workbook checksum, and never commit or push. | IAM-073 | Plan mode prints the exact generated prompt without invoking Codex; execution requires an explicit flag; dirty repositories and main/master branches are rejected; unsafe or unresolved task paths remain rejected; Codex output and exit code are captured; workbook checksum remains unchanged; no automatic commit, push, or tracker update occurs; unit tests cover prompt creation, argument construction, Git preflight, execution failure, and dry-run behavior. | Done
CODE-044 | Frontend | web | apps/web/package.json; apps/web/app/layout.tsx; apps/web/app/page.tsx | Initialize Next.js frontend application | Initialize apps/web as a pnpm-managed Next.js application using TypeScript, App Router, Tailwind CSS, and ESLint. Keep the app directory at apps/web/app rather than apps/web/src/app so existing tracker paths remain valid. Inspect the root workspace scripts and choose a package name compatible with dev:web. Preserve the existing monorepo structure. | IAM-002 | Next.js application exists under apps/web; package participates in the pnpm workspace; layout and home page render; Tailwind and ESLint are configured; root dev:web resolves the package; web build passes. | Done
CODE-045 | Database | supabase | supabase/config.toml | Initialize local Supabase configuration | Initialize repository-local Supabase configuration without secrets. Create supabase/config.toml using safe local-development settings and the standard migration directory expected by the project. Do not provision a hosted Supabase project, access credentials, configure production values, or create database migrations. Hosted-project creation, connection-string configuration, database reachability, and external connection verification remain manual IAM-006 completion requirements. | IAM-006 | supabase/config.toml exists; it contains no credentials, tokens, passwords, or production secrets; local Supabase project and migration discovery settings are configured; the repository structure supports the documented local migration workflow; configuration syntax is valid; and no hosted Supabase project or database migration is created. | Done
CODE-046 | Database | migrations | supabase/migrations/20260804164436_audit_trigger.sql | Create reusable audit trigger migration | Create an ordered PostgreSQL migration that defines reusable audit timestamp behavior for IAMONIT tables. Define a reusable trigger function that sets updated_at to the current timestamp whenever a row is updated. Use timestamptz for created_at and updated_at conventions. Keep the migration compatible with Supabase PostgreSQL and safe to apply through the existing local migration workflow. Do not create tenants, app_users, authentication endpoints, or unrelated tables in this task. Do not apply the migration to the hosted Supabase project automatically. | IAM-007 | supabase/migrations/20260804164436_audit_trigger.sql exists; it defines a reusable PostgreSQL updated_at trigger function; audit timestamp conventions use timestamptz; the SQL is valid and safely ordered; the migration applies successfully to the local Supabase database; local verification confirms that a table using the trigger receives a changed updated_at value after an update; no unrelated tables are created; and no hosted-project migration is applied. | Done
CODE-047 | Database | migrations | supabase/migrations/20260804234822_create_app_users.sql | Create app_users migration | Create one ordered, timestamped Supabase PostgreSQL migration for public.app_users. Define id as uuid primary key referencing auth.users(id), with no generated default and ON DELETE CASCADE, so each Supabase authentication identity has at most one application profile. Define tenant_id as uuid NOT NULL referencing public.tenants(id) with ON DELETE RESTRICT, modeling one tenant per app user. Define role as text NOT NULL with an exact check constraint allowing only: - admin - dispatcher - car_puller Define full_name and phone as text NOT NULL. Do not duplicate authentication email and do not add status, membership, invitation, or separate profile fields. Add created_at and updated_at as timestamptz NOT NULL DEFAULT now(). Add created_by and updated_by as nullable uuid columns without foreign keys at this stage. Attach a BEFORE UPDATE trigger that executes public.set_updated_at(). Add an index on tenant_id. Enable row-level security, but do not create access policies because app-user and tenant policies belong to IAM-014. Do not modify authentication, API, frontend, invitation, profile, membership, or other application files. Apply and verify only against the local Supabase database. Do not apply the migration to the hosted project. | IAM-011 | The timestamped migration creates public.app_users with id, tenant_id, role, full_name, phone, created_at, updated_at, created_by, and updated_by. id is a uuid primary key referencing auth.users(id), has no generated default, and uses ON DELETE CASCADE. Inserting an app-user requires an existing auth user, and duplicate profiles for one authentication identity are rejected. tenant_id is required, references public.tenants(id), and uses ON DELETE RESTRICT. role is required and accepts only admin, dispatcher, or car_puller. Invalid role values are rejected. full_name and phone are required. created_at and updated_at use timestamptz NOT NULL DEFAULT now(). created_by and updated_by are nullable uuid columns without foreign keys. A BEFORE UPDATE trigger invokes public.set_updated_at(), and updating a profile changes updated_at. An index exists on tenant_id. RLS is enabled without adding IAM-014 access policies. The migration applies successfully to the local Supabase database. Privileged local verification confirms: - A valid linked app-user can be inserted. - An invalid auth-user ID is rejected. - An invalid tenant ID is rejected. - A duplicate auth-user ID is rejected. - An invalid role is rejected. - updated_at advances after an update. No membership, invitation, API, frontend, or unrelated tables or files are created, and no hosted-project migration is applied. | Done

## File-Class Map
Area | Path | Purpose | Primary Related Tasks | Build Order
Backend | apps/api/src/config/env.config.ts; apps/api/src/app.module.ts; apps/api/.env.example; apps/web/.env.example | Complete environment configuration and validation | IAM-004 | CODE-001
Backend | apps/api/src/modules/auth/dto/register.dto.ts | Create RegisterDto | IAM-008 | CODE-002
Backend | apps/api/src/modules/auth/dto/login.dto.ts | Create LoginDto | IAM-008 | CODE-003
Backend | apps/api/src/common/supabase/supabase.constants.ts; apps/api/src/common/supabase/supabase.provider.ts; apps/api/src/common/supabase/supabase.module.ts; apps/api/src/common/supabase/supabase.provider.spec.ts; apps/api/src/modules/auth/auth.types.ts; apps/api/src/modules/auth/dto/auth-response.dto.ts; apps/api/src/modules/auth/dto/register.dto.ts; apps/api/src/modules/auth/auth.module.ts; apps/api/package.json; ././pnpm-lock.yaml | Create authentication integration foundation | IAM-015,IAM-016 | CODE-048
Backend | apps/api/src/modules/auth/auth.service.ts; apps/api/src/modules/auth/auth.repository.ts; apps/api/src/modules/auth/auth.service.spec.ts; apps/api/src/modules/auth/auth.repository.spec.ts | Implement company registration orchestration | IAM-015 | CODE-005
Backend | apps/api/src/modules/auth/auth.service.ts; apps/api/src/modules/auth/auth.repository.ts; apps/api/src/modules/auth/auth.service.spec.ts; apps/api/src/modules/auth/auth.repository.spec.ts | Implement login service and user context | IAM-016 | CODE-049
Backend | apps/api/src/modules/auth/auth.controller.ts; apps/api/src/modules/auth/auth.controller.spec.ts | Implement register and login controllers | IAM-015,IAM-016 | CODE-004
Backend | apps/api/src/modules/auth/jwt.strategy.ts | Implement JWT strategy | IAM-016 | CODE-006
Backend | apps/api/src/common/guards/auth.guard.ts | Create auth guard | IAM-018 | CODE-007
Backend | apps/api/src/common/guards/roles.guard.ts | Create role guard | IAM-018 | CODE-008
Backend | apps/api/src/modules/tenants/tenants.service.ts | Create tenant service | IAM-025 | CODE-009
Backend | apps/api/src/modules/users/users.controller.ts | Build users controller | IAM-022 | CODE-010
Backend | apps/api/src/modules/users/users.service.ts | Build users service | IAM-022 | CODE-011
Backend | apps/api/src/modules/invitations/invitations.controller.ts | Build invitation endpoints | IAM-020,IAM-021 | CODE-012
Backend | apps/api/src/modules/invitations/invitations.service.ts | Implement token creation/acceptance | IAM-020,IAM-021 | CODE-013
Backend | apps/api/src/modules/tasks/dto/create-task.dto.ts | Create CreateTaskDto | IAM-028 | CODE-014
Backend | apps/api/src/modules/tasks/tasks.controller.ts | Implement task CRUD endpoints | IAM-029,IAM-030,IAM-031 | CODE-015
Backend | apps/api/src/modules/tasks/tasks.service.ts | Implement task business logic | IAM-029,IAM-030,IAM-031 | CODE-016
Backend | apps/api/src/modules/tasks/task-status.service.ts | Implement status transitions | IAM-032 | CODE-017
Backend | apps/api/src/modules/uploads/uploads.controller.ts | Build signed URL endpoint | IAM-037 | CODE-018
Backend | apps/api/src/modules/uploads/uploads.service.ts | Generate tenant-scoped storage paths | IAM-037 | CODE-019
Backend | apps/api/src/modules/task-updates/task-updates.controller.ts | Build task update endpoint | IAM-041 | CODE-020
Backend | apps/api/src/modules/notifications/notifications.service.ts | Emit notification records | IAM-045 | CODE-021
Frontend | apps/web/app/(auth)/login/page.tsx | Build login page | IAM-009 | CODE-022
Frontend | apps/web/app/(auth)/register/page.tsx | Build registration page | IAM-009 | CODE-023
Frontend | apps/web/lib/api.ts | Create API client | IAM-017 | CODE-024
Frontend | apps/web/lib/auth.ts | Create auth helpers | IAM-017 | CODE-025
Frontend | apps/web/components/layout/Sidebar.tsx | Build sidebar navigation | IAM-024 | CODE-026
Frontend | apps/web/components/layout/Topbar.tsx | Build topbar | IAM-024,IAM-047 | CODE-027
Frontend | apps/web/app/(dashboard)/tasks/page.tsx | Build task list page | IAM-033,IAM-051 | CODE-028
Frontend | apps/web/app/(dashboard)/tasks/new/page.tsx | Build create task page | IAM-034 | CODE-029
Frontend | apps/web/app/(dashboard)/tasks/[id]/page.tsx | Build task detail page | IAM-035 | CODE-030
Frontend | apps/web/components/tasks/TaskTimeline.tsx | Build timeline component | IAM-042 | CODE-031
Frontend | apps/web/components/uploads/FileUploader.tsx | Build file uploader | IAM-039 | CODE-032
Frontend | apps/web/app/(dashboard)/my-tasks/[id]/page.tsx | Build mobile execution page | IAM-043 | CODE-033
Frontend | apps/web/components/notifications/NotificationBell.tsx | Build notification dropdown | IAM-047 | CODE-034
Database | supabase/migrations/20260804165923_create_tenants.sql | Create tenants migration | IAM-010 | CODE-035
Database | supabase/migrations/026_tasks.sql | Create tasks migration | IAM-026 | CODE-036
Database | supabase/migrations/014_rls_core.sql | Create core RLS policies | IAM-014 | CODE-037
Database | supabase/migrations/036_storage.sql | Create storage policies | IAM-036 | CODE-038
QA | apps/api/test/tasks.spec.ts | Write task service tests | IAM-056 | CODE-039
QA | e2e/iamonit-mvp.spec.ts | Write E2E MVP test | IAM-058 | CODE-040
Database | supabase/config.toml | Initialize local Supabase configuration | IAM-006 | CODE-045
Database | supabase/migrations/20260804164436_audit_trigger.sql | Create reusable audit trigger migration | IAM-007 | CODE-046
Database | supabase/migrations/20260804234822_create_app_users.sql | Create app_users migration | IAM-011 | CODE-047

## API Contracts
Method | Endpoint | Purpose | Role Access | Request Body / Params | Response | Related Tasks
POST | /auth/register | Register new company admin or invited user | Public | email,password,role,company/profile fields | session + user context | IAM-015,IAM-017
POST | /auth/login | Authenticate user | Public | email,password | session + user context | IAM-016,IAM-017
GET | /users | List tenant users | Admin | query: page,search | users[] | IAM-022,IAM-023
POST | /invitations | Invite user to tenant | Admin | email,role | invitation | IAM-020
POST | /invitations/accept | Accept invite | Public/Auth | token,password/profile fields | user joined tenant | IAM-021
GET | /tasks | List tasks by tenant/role | Admin,Dispatcher,Car Puller | status,search,page,date range | tasks[] | IAM-030,IAM-033,IAM-050
POST | /tasks | Create task | Admin,Dispatcher | assignedTo,notes,priority,workOrderFileId | task | IAM-029,IAM-034
GET | /tasks/:id | Get task detail | Tenant user with access | task id | task + updates + history | IAM-031,IAM-035
PATCH | /tasks/:id/status | Update task status | Assigned role/user | status,note | updated task | IAM-032,IAM-043
POST | /uploads/signed-url | Get signed upload URL | Authenticated | fileName,mimeType,size,taskId | signedUrl,filePath | IAM-037,IAM-039
POST | /tasks/:id/updates | Create note/media update | Tenant user with access | type,note,fileIds | task update | IAM-041,IAM-042
GET | /notifications | List notifications | Authenticated | page,unreadOnly | notifications[] | IAM-046,IAM-047
PATCH | /notifications/:id/read | Mark read | Authenticated | id | notification | IAM-046,IAM-047

## DB Schema + RLS
Table | Purpose | Key Columns | Tenant/RLS Rule | Audit Fields | Related Tasks
tenants | Company/tenant container | id,name,status | Admin can access own tenant | created_at,updated_at,created_by,updated_by | IAM-010,IAM-014
app_users | User profile linked to auth.users | id,tenant_id,role,full_name,phone | Users can see tenant users by policy/admin rules | created_at,updated_at,created_by,updated_by | IAM-011,IAM-014
transporter_profiles | Transporter company/dispatch/broker info | tenant_id,company_name,dispatch_name,broker_name | tenant_id = current user tenant | created_at,updated_at,created_by,updated_by | IAM-012,IAM-025
car_puller_profiles | Car puller profile and photo/logo | user_id,tenant_id,photo_url,logo_url | tenant_id = current user tenant | created_at,updated_at,created_by,updated_by | IAM-013
invitations | Tenant user invitation tokens | tenant_id,email,role,token,expires_at,accepted | Admin only create/list; token accept flow | created_at,updated_at,created_by,updated_by | IAM-019-IAM-021
tasks | Work orders/tasks | tenant_id,created_by,assigned_to,status,notes,priority | Tenant users; car puller assigned only | created_at,updated_at,created_by,updated_by | IAM-026-IAM-032
task_status_history | Audit trail of task status changes | task_id,from_status,to_status,changed_by | Via parent task tenant | created_at,created_by | IAM-027,IAM-032
files | Uploaded file metadata | tenant_id,task_id,path,mime_type,size_bytes | tenant-scoped storage path and policy | created_at,updated_at,created_by,updated_by | IAM-038
task_updates | Timeline notes/images/videos | tenant_id,task_id,type,note,file_id | Via task tenant and user access | created_at,updated_at,created_by,updated_by | IAM-040,IAM-041
notifications | User notifications | tenant_id,user_id,type,read_at,payload | user_id = auth.uid() and tenant_id matched | created_at,updated_at | IAM-044-IAM-047
audit_logs | Sensitive business events | tenant_id,actor_id,entity_type,entity_id,action | Admin/security only by tenant | created_at,created_by | IAM-053

## UI Screens
Screen Code | Screen | Route | Role | Purpose | Components | Related Tasks | Status
UI-001 | Login | /login | All | Authenticate existing users | LoginForm | IAM-009,IAM-017 | Todo
UI-002 | Register | /register | All | Register new tenant/admin or car puller | RegisterForm,RoleSelector | IAM-009,IAM-017 | Todo
UI-003 | Dashboard | /dashboard | Admin/Dispatcher | Show KPIs and recent activity | KpiCard,RecentTasks | IAM-048 | Todo
UI-004 | My Tasks | /my-tasks | Car Puller | Show assigned tasks | TaskCard,TaskFilters | IAM-049 | Todo
UI-005 | Task List | /tasks | Admin/Dispatcher | Manage/search all tenant tasks | TaskTable,TaskFilters | IAM-033,IAM-051 | Todo
UI-006 | Create Task | /tasks/new | Admin/Dispatcher | Create work order and assign car puller | CreateTaskForm,FileUploader | IAM-034,IAM-039 | Todo
UI-007 | Task Detail | /tasks/[id] | All with access | View/update task and timeline | TaskDetail,TaskTimeline,StatusActions | IAM-035,IAM-042 | Todo
UI-008 | Execution Screen | /my-tasks/[id] | Car Puller | Mobile-first execution controls | TaskUpdateComposer,StatusActions | IAM-043 | Todo
UI-009 | Users | /users | Admin | Invite/manage tenant users | UserTable,InviteUserModal | IAM-023 | Todo
UI-010 | Company Settings | /settings/company | Admin | Update transporter profile | CompanySettingsForm | IAM-025 | Todo
UI-011 | Notification Bell | Global Topbar | All | Show alerts and read status | NotificationBell | IAM-047 | Todo

## Risks & Decisions
ID | Type | Risk / Decision | Impact | Mitigation / Decision | Owner | Status
R-001 | Risk | Cross-tenant data leak | Critical | Use RLS, backend tenant middleware, automated tests | Security | Open
R-002 | Risk | Large video uploads fail or cost too much | High | Use signed URLs, file limits, compression guidance, storage lifecycle rules | Backend | Open
R-003 | Risk | Unclear payment ownership between transporter and car puller | Medium | Start with manual paid status; design Stripe later | Product | Open
R-004 | Risk | Scope creep before MVP | High | Freeze Sprint 1-8 as MVP; push GPS/payments/realtime to future | Product | Open
D-001 | Decision | Use single database with tenant_id | High | Best MVP balance; use RLS for isolation | Architecture | Accepted
D-002 | Decision | Use timestamptz for all dates | High | Avoid timezone bugs; store UTC, display local | Database | Accepted

## Release Checklist
Area | Checklist Item | Required for MVP? | Owner | Status | Evidence / Link
Security | RLS tested for tenant isolation | Yes | Security | Todo
Auth | Register/login/logout working in production | Yes | Backend | Todo
Tasks | Transporter can create and assign a task | Yes | Fullstack | Todo
Execution | Car puller can accept/start/upload/complete | Yes | Frontend | Todo
Uploads | PDF/image/video uploads work | Yes | Fullstack | Todo
Notifications | Task assignment notification works | No | Fullstack | Todo
Testing | E2E MVP flow passes | Yes | QA | Todo
Deployment | Frontend deployed with prod env vars | Yes | DevOps | Todo
Deployment | Backend deployed with SSL and CORS | Yes | DevOps | Todo
Docs | User guide created | No | Product | Todo